## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

TEAM NAME	TEAM-18
PROJECT NAME	Convert webERP to web 2.0 type UI using Laravel
PROJECT MENTOR	Mr. Shreekanth Puram
TEAM MEMBERS	Yash Khandelwal
	Yash Patel
	Kartavya Gupta
	Sachin Sharma

## Team_Status
TEAM NAME	TEAM-18
PROJECT NAME	Convert webERP to web 2.0 type UI using Laravel
PROJECT MENTOR	Mr. Shreekanth Puram

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 6 (sept 5- sept 11)
Learn Laravel	Preparation	Yash Khandelwal	16	28	Ongoing	Learning laravel is necessary to start with our project	-12	42.8571428571
Role preferences	Coordination	Sachin	4	2	Done		2	100
SVN Repository setup	Preparation	Yash Patel	1	1.5	Ongoing		-0.5	33.3333333333
Discuss bug report software	Preparation	Yash Patel	2	4	Delayed	This is critical to project success	-2	50
Develop questions for requirements elicitation	Documentation	Kartavya	4	8	Planned	Make sure scoping questions are included	-4	50
Get account and configure website	Preparation	Yash	4	3.5	Done		0.5	14.2857142857
Research existing technology	Preparation	Yash Patel	4	4	Ongoing		0	0
Project synopsis writeup	Documentation	Yash Patel	3.2	8	Done		-4.8	60
Identify role owners	Preparation	Yash Khandelwal	2	2	Done	Multiple roles are OK - think about role & reponsibility distribution	0	0
Team Meeting	Coordination	Yash Khandelwal	3	8	Done		-5	62.5
Status tracker	Documentation	Yash Khandelwal	1.6	1.6	Planned		0	0
Modifying SRS	Documentation	Yash Patel	6	6	Done	2	0	0
Documenting meetings	Documentation	Yash Patel	2	2	Done	0	0	0
Week 7 (sept 12 - sept 18)
Understanding Sample Code	Preparation	Yash Patel	8	8	Ongoing	Sample Code given by Client	0	0
Understanding raw php code of System Parameters module	Preparation	Yash Khandelwal	4	3.75	Done	Functionalities of code is to be kept same	0.25	6.6666666667
Coding System Parameters Module in Laravel framework basic	Development	Yash Patel	12	10	Done		2	20
Team Meeting	Coordination	Kartavya	4	8	Done		-4	50
Status Tracker	Testing	Yash Khandelwal	1	9.5	Delayed		-8.5	89.4736842105
Fixing bug for saving into database	Documentation	Yash Patel	7	8	Done		-1	12.5
Documenting meetings	Documentation	Yash Khandelwal	2	2	done
Implementing final system parameter module	Development	Yash Patel	5	5	Done
Week 8 (sept 19 - sept 25)
Understanding Inventory Module	Preparation	Yash Khandelwal	8	7	Done		1	14.2857142857
Paper Design of Inventory Module	Design	Yash Patel	8	6	Delayed		2	33.3333333333
Implement basics of Inventory Module	Development	Sachin	12	7	Done
Discussing Bugs	Testing	kartavya	6	2.5	Done
Team Meeting	Coordination	kartavya	4	4	Done
Status Tracker	Documentation	Yash Khandelwal	1.6	1.6	Done		0	0
ImplementAdd categories.	Development	Yash Khandelwal	5	7	done
Implement Add Items.	Development	Yash Patel	5	7	done
Test Plan	Documentation	Yash Khandelwal	2	2	done
Documenting meetings	Documentation	Yash Patel	2	2	done
Week 9
Implementing suppliers	Development	Yash Khandelwal	5	7	Done		-2	28.5714285714
Design Document	Documentation	Yash Patel	9	9	Done
Team Meeting	Coordination	kartavya	4	4.5	Done
Discussing Bugs	Testing	Sachin	4	4	Done
Understanding Purchase Module	Preparation	Yash Khandelwal	7	5	Done
Updating SRS	Documentation	Yash Patel	4	5	Done		-1	20
Merging codes	Development	Yash Patel	3	3	Done
Documenting meetings	Documentation	Yash Khandelwal	2	2	done
Week 10
Implementing add_purchase_order	Development	Yash Khandelwal	10	14	done		-4	28.5714285714
Using Google Api for country names and date	Development	Yash Patel	4	5	done
Status Tracker	Documentation	kartavya	1.6	1.6	Done		0	0
Discussing Bugs	Testing	Yash Khandelwal	5	6	done		-1	16.6666666667
Implement price with specific suppliers	Development	Yash Patel	4	5	done
Implement list of items	Development	Yash Patel	2	3	done
Implement add locations	Development	Yash Patel	2	3	done
Google API Intregation	Development	Yash Patel	1	1	done
Documenting meetings	Documentation	yash patel	2	2	done
Week 11
Code Review	Development	kartavya	12	10	Done		2	20
Document Review	Documentation	Sachin	12	8	Done		4	50
Merging codes	Development	yash patel	2	2	Done		0	0
Fixing bugs	Development	Yash Khandelwal	16	12	Done
Making presentation for R1	Preparation	Sachin	9	9.5	Done
Practice for presentation	Coordination	kartavya	4	8	Done
Week 12

R1 presentation and mid-sems					Done

Week 13
Improving Purchase Order module	Development	Yash Khandelwal	2	4	Done		-2	50
view of paced orders	Development	Sachin	2	3	Done		-1	33.3333333333
Filling Documents	Documentation	yash patel	8	8	Done		0	0
Placed Orders (bugs)	Testing	kartavya	1	1	Done		0	0
Stocks Module	Development	Yash Khandelwal	3	5	Done
Week 14
Revising Documents	Documentation	kartavya	4	4	Done		0	0
Team Meeting	Coordination	yash patel	4	4	Done		0	0
PDF/Export	Development	Yash Khandelwal	1	3	Done		-2	66.6666666667
Code Review	Testing	yash patel	4	4	Done
sales module	Development	kartavya	3	5	Done		-2	40
Week 15
Bug fixing in Purchase Order module	Testing	Yash Khandelwal	2	2	Done		0	0
Changing UI	Development	Yash Khandelwal	8	11	Ongoing		-3	27.2727272727
Team Meeting	Coordination	yash patel	2	4	Done		-2	50
Bug Fixing	Testing	yash patel	4	5	Ongoing
Grant Privileges module	Development	Yash Khandelwal	3	4	Done
Filling Documents	Documentation	Yash Khandelwal	8	6	Done
Sales Module	Development	yash patel	4	7	Done
Bug Fixing of sales module	Testing	yash patel	2	2	Ongoing
Week 16

Week 17

## Individual_Status
TEAM NAME	TEAM-18
PROJECT NAME	Convert webERP to web 2.0 type UI using Laravel
PROJECT MENTOR	Mr. Shreekanth Puram

Actvities	Yash Khandelwal		Yash Patel		Kartavya Gupta		Sachin Sharma		0		Estimated Total Hours	Actual Total Hours
	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent
Week 6 (sept 5- sept 11)
Learn Laravel	4	8	4	9	4	5	4	6			16	28
Role preferences	1	0.5	1	0.5	1	0.5	1	0.5			4	2
SVN Repository setup	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5			2	2
Discuss bug report software	0.5	1	0.5	1	0.5	1	0.5	1			2	4
Develop questions for requirements elicitation	1	2	1	2	1	2	1	2			4	8
Get account and configure website	1	1	1	0.5	1	1	1	1			4	3.5
Research existing technology	1	1	1	1	1	1	1	1			4	4
Project synopsis writeup	0.8	2	0.8	2	0.8	2	0.8	2			3.2	8
Identify role owners	0.5	0.5	0.5	0.5	0.5	0.5	0.5	0.5			2	2
Team Meeting	0.75	2	0.75	2	0.75	2	0.75	2			3	8
Status tracker	0.4	0.4	0.4	0.4	0.4	0.4	0.4	0.4			6	1.6
Modifying SRS	2	2	2	2	2	2	0	0
Documenting meetings	0	0	2	2	0	0	0	0
Week 7 (sept 12 – sept 18)
Understanding Sample Code	2	3	2	3	2	1	2	1			8	8
Understanding raw php code of System Parameters module	1	0.75	1	1	1	1	1	1			4	3.75
Coding System Parameters Module in Laravel framework basic	3	3.5	5	7	3	2	3	2			14	14.5
Team Meeting	1	2	1	2	1	2	1	2			4	8
Status Tracker	0.4	0.4	0.4	0.4	0.4	0.4	0.4	0.4			1.6	1.6
Fixing bug for saving into database	3	3	4	5	0	0	0	0
Documenting meetings	2	2	0	0	0	0	0	0
Implementing final system parameter module	0	0	5	5	0	0	0	0
Week 8 (sept 19 - sept 25)
Understanding Inventory Module	2	2	2	2	2	1.5	2	2			8	7
Paper Design of Inventory Module	2	2	2	2	2	1.5	2	1			8	6
Implement basics of Inventory Module	3	4	3	4	3	1	3	1			12	7
Discussing Bugs	1.5	1	1.5	1	1.5	0.5	1.5	0.5			6	2.5
Team Meeting	1	1	1	1	1	1	1	1			4	4
Status Tracker	0.4	0.4	0.4	0.4	0.4	0.4	0.4	0.4			1.6	1.6
ImplementAdd categories.	5	7	0	0	0	0	0	0
Implement Add Items.	0	0	5	7	0	0	0	0
Test Plan	2	2	0	0	0	0	0	0
Documenting meetings	0	0	2	2	0	0	0	0
Week 9 (sept 26 – oct 1)
Implementing suppliers	5	7	0	0	0	0	0	0			5	7
Design Document	3	4	3	3	2	2	2	2			9	9
Team Meeting	1	3	1	3	1	0.5	1	0.5			4	4.5
Discussing Bugs	1	1	1	1	1	1	1	1			4	4
Understanding Purchase Module	1	0.5	1	0.5	2	1.5	2	1.5			7	5
Updating SRS	1	2	1	2	1	1	1	1			4	5
Merging codes	0	0	3	3	0	0	0	0			3	3
Documenting meetings	2	2	0	0	0	0	0	0			2	2
Week 10 (oct 2 – oct 8)						0	0
Implementing add_purchase_order	8	12	2	2	0	0	0	0			10	14
Using Google Api for country names and date	0	0	4	5	0	0	0	0			4	5
Status Tracker	0.4	0.4	0.4	0.4	0.4	0.4	0.4	0.4			1.6	1.6
Discussing Bugs	1.5	2	1.5	2	1	1	1	1			5	6
Implement price with specific suppliers	0	0	4	5	0	0	0	0			4	5
Implement list of items	0	0	2	3	0	0	0	0			2	3
Implement add locations	0	0	2	3	0	0	0	0			2	3
Google API Intregation	0	0	1	1	0	0	0	0			1	1
Documenting meetings	0	0	2	2	0	0	0	0			2	2
Week 11 (oct 9 – oct 16)						0	0
Code Review	3	3	3	3	3	2	3	2			12	10
Document Review	4	4	4	4	2	0	2	0			12	8
Merging codes	0	0	2	2	0	0	0	0			2	2
Fixing bugs	4	4	4	4	4	2	4	2			16	12
Making presentation for R1	3	3	3	3	1.5	1.5	1.5	2			9	9.5
Practice for presentation	1	2	1	2	1	2	1	2			4	8
Bug fixing in Purchase Order module						0	0
Changing UI						0	0
Team Meeting						0	0
Week 12 (oct 17 – oct 24)						0	0
R1 presentation and mid-sems						0	0
						0	0
Week 13 (oct25- nov2) {diwali break}						0	0
Improving Purchase Order module	2	4	0	0	0	0	0	0			2	4
view of paced orders	0	0	0	0	0	0	2	3			2	3
Filling Documents	2	2	2	2	2	2	2	2			8	8
Placed Orders (bugs)	1	1	0	0	0	0	0	0			1	1
Stocks Module	3	5	0	0	0	0	0	0			3	5
						0	0
Week 14 (nov 3- nov9)						0	0
Revising Documents	1	2	1	2	1	0	1	0			4	4
Team Meeting	1	1	1	1	1	1	1	1			4	4
PDF/Export	1	3	0	0	0	0	0	0			1	3
Code Review	1	1.5	1	1.5	1	0.5	1	0.5			4	4
sales module	0	0	0	0	3	5	0	0			3	5

Week 15(nov 9 – nov 16)						0	0
Bug fixing in Purchase Order module	2	2	0	0	0	0	0	0			2	2
Changing UI	8	11	0	0	0	0	0	0			8	11
Team Meeting	1	2	1	2	0	0	0	0			2	4
Bug Fixing	2	3	2	3	1	1	1	1			6	8
Grant Privileges module	3	4	3	4	0	0	0	0			6	8
Filling Documents	2	2	2	2	2	2	2				8	6
Sales Module	0	0	4	7	0	0	0	0			4	7
Bug Fixing in sales module	0	0	2	2	0	0	0	0			2	2
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
0						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0
						0	0